National Delivery Plan Year 2 Financial Update: Quarter 4

Paediatric Telehealth

Summary:

Total allocated 2009/10 : £336,000 Predicted spend Q4: £174,647 Actual spend Q4: £ 162,706 Spend in Q4 against predicted spend (as +/- %): - 7% Cumulative spend to date: £347,635 Money remaining: £13,706 Slippage as at Q4: £11,206 Number of vacant posts (including those being covered by locums, additional hours etc.): 0

| Staffing | Appointed? Y/N | Q1 Spent | Q2 Projected | Q2 Spent | Q3 Projected | Q3 Spent | Q4 Projected | Q4 Spent | Total Spent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Date of appointment |  |  |  |  |  |  |  |  |
| Technical support AfC 6 | Contract from Sept 2006 | 8850 | 9219 | 9000 | 9291 | 10082 | 9291 | 9291 | 36432 |
| Technical support AfC 5 | Jun-09 | 2306 | 6918 | 6918 | 6918 | 7573 | 6918 | 7076 | 23060 |
| Clinical facilitators AfC 7 x2.5 | Oct -09, Oct-09, Nov-09 | 0 | 0 | 0 | 25703 | 23140 | 27438 | 23049 | 53141 |
| Clinical Lead | Jan-10 | 0 | 0 | 0 | 2500 | 0 | 2500 | 0 | 0 |
| Total Staffing |  | 11156 | 16137 | 15918 | 44412 | 40795 | 46147 | 39416 | 107285 |
| Equipment |  |  |  |  |  |  |  |  |  |
| Children's Hospitals |  | 27507 | 0 | 0 | 0 | 0 | 20000 | 20201 | 47708 |
| Equipment upgrades |  | 0 | 0 | 19268 | 0 | 0 | 0 | 0 | 19268 |
| Tier 2 sites |  | 11845 | 10000 | 744 | 20000 | 10132 | 30000 | 27954 | 50675 |
| Remote and Rural |  | 0 |  | 0 | 30000 | 18755 | 42000 | 50656 | 69411 |
| Care at Home |  | 0 | 5000 | 2371 | 10000 | 0 | 20000 | 6815 | 9186 |
| Other |  |  |  |  |  |  |  |  |  |
| Communication costs |  | 4136 |  | 0 | 1000 | 0 | 2000 | 0 | 4136 |
| Maintenance |  | 3060 | 5000 | 1493 | 5000 | 2131 | 10000 | 14432 | 21116 |
| Office costs |  | 427 | 1000 | 1378 | 3000 | 3470 | 1000 | 1891 | 7166 |
| Travel |  | 332 | 1000 | 384 | 2000 | 615 | 2000 | 1341 | 2672 |
| Training |  |  |  |  | 1500 | 8550 | 1500 | 0 | 8550 |
| Total Equipment / Other |  | 47424 | 22000 | 25984 | 72500 | 43653 | 128500 | 123290 | 240350 |
| Total overall spent/ predicted |  | 58579 | 38137 | 41902 | 116913 | 84448 | 174647 | 162706 | 347635 |

Commentary (please provide explanation of spending to date): Current budget Underspend from 2008/9 (est £10k) 15152 Equipment carry forward from 2008/9 (Tayside YP Unit, Tayside Comms, Yorkhill Telemed) 48500 NDP allocation Year 2 336000 Total 399652 Est Underspend 38311 Spend to date 347635 Carry Forward Clinical Lead 2500 Balance Remaining 11206 Clinical lead appointed from 1st January 2010-02-03. Payrolls issues have delayed payment therefore estimated spend carried forward. Staffing costs in line with expectations, however staff expenses coded to staffing costs hence some under spend in travel allocation. Telemed Nurse Specialist resigned in Q4, hence some under spend in nursing budget. Equipment spend in Q4 in line with revised predictions.

Installation Progress

| YP Unit Edinburgh | Mobile System | ISDN lines now on order by NHS Lothian |
| --- | --- | --- |
| YP Unit Tayside | Mobile System | Equipment delivered to site, awaiting installation of network upgrade by NHS Tayside |
| Stirling Royal | IP Testing | Installation complete |
| RHSC Edinburgh | Comms Upgrade | ISDN lines now on order by NHS Lothian |
| Forth Park | Intern Upgrade | Installation complete |
| Western Isles | Intern | Installation complete, HL to undertake system testing |
| Wick | A&E wall mounted system | Awaiting installation of data points / screen mount by local estates dept |
| Fort William | A&E mobile cart | System installed on site, user changed requirements and requested swap. In progress |
| Orkney | A&E / Paedie Sea Centre | Installation complete |
| Shetland | A&E | Installation in progress |
| Oban | Paediatrics Dept | Installation TBA |
| Elgin | Paediatrics Dept | Installation TBA |

Progress

Technical

National equipment rollout progressing well and on schedule for completion in 2010/11

22 systems installed and a further 6 upgraded with a further 6 installations in progress

Technical support for multi-site conferences improved with dedicated support available within the NHS Grampian Bridging Service

Staffing

1.5 Telemedicine Nurse Specialists currently in post.  (Remaining post vacant due to resignation.  Recruitment in progress)

Clinical Lead in post

2 technical support staff in post (North and West)

Critical Decision Support

- Review of transport data undertaken

- Review of equipment requirements complete

- Equipment installed / on order for all remote and rural DGHs

- Agreement reached with lead PICU consultants on proposed methodology

Unscheduled Care

- Equipment installed / on order for all remote and rural DGHs

- Equipment installed in Raigmore / Aberdeen Children’s Hospital

- Some progress made in engagement with clinicians, however work plan delayed due to staff vacancy

Care at Home

Lead clinicians recruited and agreement reached on project outline

Equipment testing complete, agreement reached on using Tandberg Movi and laptops in conjunction with NHS Grampian

Laptops, webcams and software licenses purchased

Evaluation framework agreed and pro-formas developed

Child Protection

Agreement reach with lead clinicians on East and West on work plan

  - To assess the suitability of using video conference to support forensic examinations

  - To review legal and ethical frameworks

  - Depending on the outcome of the above, to assist in the development of a telemedicine enhanced service model and associated business case

Provision of ongoing support to Child Protection MCN meetings and peer review sessions

CAMHS

Agreement reached within the North to pilot the use of video conferencing to support CAHMS education programme

Project outline agreed

Final protocol and evaluation framework for the CAMHS study agreed

Allocation of local staffing resource to develop project agreed.

Equipment installation complete, staff training to be undertaken

Clinical Network

- Continuing support provided for clinical networks including:

  - The Children and Teenagers Scottish Cancer Network (CATSCAN)

  - Child and Adolescent Mental Health Services

  - Children with Severe and Complex Mental Health Needs

  - West Child Protection Network

  - East Child Protection Network

  - Rheumatology Network

  - Scottish Paediatric Endocrine Group MCN (SPEG)

  - Inherited Metabolic Diseases Network (IMD)

  - Leukaemia and Bone Marrow Transplant MDT

  - Scottish Muscle Network

  - Neonatal Journal Club

  - Palliative Care Network

  - Renal and Urology Network

  - Scottish Neonatal Consultants Group (SNCG)

  - Scottish Genital Anomalies Network (SGAN)

  - West Paediatric Gastroenterology, Hepatology and Nutrition Network

  - Paediatric Epilepsy

  - Complex Respiratory

Other

Babycam systems installed and operational in Ninewells and Southern General

On-site technical training provided as required

System documentation developed and available on-line

Continuing support provided for clinical education programmes at RHSC Edinburgh, RHSC Glasgow, Ninewells and RCPCH