The North of Scotland – NDP status report re investment

November 2009-

National Delivery Plan Year 2 f

| Number | Activity | Elements | Status | Proposed outcomes | Achieved outcomes | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | Infra-structure |  |  |  |  |  |
|  |  | Programme manager | Y – appointed April 1st 09 | Support development of NoS NDP plans | Implementation plans in place for y1&2 Draft year 3 plan being complied |  |
|  |  | Clinical leads | Y | Provide clinic leadership for child health in the North of Scotland | Has established a Clinical Reference group |  |
|  |  | Public Health support |  | Development of evaluation mechanism, to show added value of investment | Logic model has been to support development and evaluation. | Tool kit to support implementation of logic model has been developed. |

| Number | Activity | Elements | Status | Proposed outcomes | Achieved outcomes | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| 2. | Gastroenterology |  |  |  |  |  |
|  |  | Network Manager | In recruitment process – but limited support has been provided to the network to support it’s development | To support the development of regional network | Limited support has been provided to progress development of Network development plan |  |
|  |  | Clinical leader | Appointed | To support the development of regional network | Providing clinical leadership to network and supporting development of NDP proposals |  |
|  |  | A&C support | Appt Sept 09 | To support the development of regional network |  |  |
|  | Grampian |  |  |  |  |  |
|  |  | Consultant Gastroenterologist | No in recruitment process Interviews 2nd November – Locum has appointed as interim measure | To support the development of regional network | Locum post has support establishment of a number of additional outreach clinics in Inverness and Islands |  |

| Number | Activity | Elements | Status | Proposed outcomes | Achieved outcomes | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| 2. | Gastroenterology |  |  |  |  |  |
|  | Grampian(cont’d) | Dietician assistant | N has been advertised |  |  |  |
|  |  | Specialist Nursing | No in recruitment process – Support is being provided by research nurse as interim measure | To support the development of regional network | Limited support is being provided to outreach clinics | This is a temporary measure until the post has been recruited to. |
|  |  | Admin | Y July 09 | To support the clinical staff |  |  |
|  |  | Psychology | Appointment as been made due to start mid october | Will provided addition support to children living with chronic health conditions |  |  |
|  | Highland |  |  |  |  |  |
|  |  | Dietician | Start at end of August 09 | To support the regional network and provide care locally | Has been supporting the outreach clinics and providing local follow-up clinics |  |
|  |  | Admin | Started May 09 |  |  |  |

| Number | Activity | Elements | Status | Proposed outcomes | Achieved outcomes | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| 2. | Gastroenterology(cont’d) |  |  |  |  |  |
|  | Tayside |  |  |  |  |  |
|  |  | Paediatrician with an interest | 1st April 09 | To support regional network and provide additional clinics. support locally | Have introduced 2 additional clinics in Perth |  |
|  |  | Consultant – Anaesthetist - Tayside | 1st April 09 | To support the regional network and provide additional anaesthetic list | Two additional anaesthetic lists are being provided per month |  |
|  |  | Dietician - Tayside | No in recruitment process |  |  |  |
|  |  | Admin – Tayside | Start date of End Sept –post covered by additional hrs |  |  |  |

| Number | Activity | Elements | Status | Proposed outcomes | Achieved outcomes | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| 3. | Neurology |  |  |  |  |  |
|  |  | Network Manager | In recruitment process – but limited support has been provided to the network to support it’s development | To support the development of regional network | Limited support has been provided to progress development of Network development plan, including guidelines and protocols |  |
|  |  | Clinical leader | Appointed | To support the development of regional network | Providing clinical leadership to network and supporting development of NDP proposals |  |
|  |  | A&C support | Appt Sept 09 | To support the development of regional network |  |  |
|  | Grampian |  |  |  |  |  |
|  |  | Specialist Nursing | N – being advertised |  |  | Has been delayed in vacancy control process |
|  |  | Physiotherapist | Y due to start October 09 | To support the development of regional network and provide local support to children and young people |  | Post holder has just started. |

| Number | Activity | Elements | Status | Proposed outcomes | Achieved outcomes | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| 3. | Neurology |  |  |  |  |  |
|  | Highland |  |  |  |  |  |
|  |  | Consultant paediatrician with an interest | No – Interviewing mid November – has been some locum cover | To support the development of regional network and provide local support to children and young people with epilepsy |  | Limited support has been provided through locum cover, primarily to support paediatric service. Full development of the role will not occur until the post holder starts |
|  |  | Specialist Nursing | Y – 3rd August 09 | Increase in provision to the service and ability to develop nurse led clinics. Allow for training to other staff | Is providing local support to children and young people , as well as contributing to the out reach service | Estimated that approximately 50 children/young people are receiving additional support. This will develop when consultant position is filled |
|  |  | Physiotherapist | Y due to start end of Sept – Additional hrs provided by service | To support the development of regional network and provide local support to children and young people | Is providing local support to children and young people , as well as contributing to the out reach service - |  |

| Number | Activity | Elements | Status | Proposed outcomes | Achieved outcomes | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| 3. | Neurology(cont’d) |  |  |  |  |  |
|  | Tayside |  |  |  |  |  |
|  |  | Paediatrician with an interest | Y freeing up consultant time | To support the development of regional network and provide local support to children and young people | Has allowed the tertiary specialist to develop network clinics, by covering local clinics |  |
|  |  | Rehab – Occupational Therapist | Y due to start Oct 09 - | To support the development of regional network and provide local support to children and young people |  |  |
|  |  | Specialist Nursing | Y - 14 Sept – Covered by additional hours | Increase in provision to the service and ability to develop nurse led clinics. Allow for training to other staff | Is providing local support to children and young people , and providing educational support to network |  |
|  |  | Admin | Y – Sept 09 cover provided by additional hours |  |  |  |

| Number | Activity | Elements | Status | Proposed outcomes | Achieved outcomes | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| 4. | Surgery |  |  |  |  |  |
|  | Grampian |  |  |  |  |  |
|  |  | Consultant Paediatric surgeon | N – in recruitment process – Locum has been appointed as interim measure | Ensure the sustainability of paediatric general surgery across the region | 6 pas of outreach time are being provided to NHS Highland, which has provided additional list and clinics. | Locum has been appointed as interim measure, which has allowed the NHS Highland development to occur and work is being progressed to establish the service with NHS Orkney and NHS Shetland. |
|  |  | Admin support | Y – Sept 09 |  |  |  |

| Number | Activity | Elements | Status | Proposed outcomes | Achieved outcomes | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| 5. | Metabolic |  |  |  |  |  |
|  | Grampian |  |  |  |  |  |
|  |  | Dietician | Y – March 09 | To support the development of the national network and provide local support to children and young people | The post has allowed for weekly specialist clinics to be established and outreach support, including education sessions for parents | The appointment to the dietetic department has been made and skill mix arrangements are in place to deliver this new service |
|  | Highland |  |  |  |  |  |
|  |  | Dietician | Y – April 09 | To support the development of the national network and provide local support to children and young people | The post has allowed the number of specialist clinics to be increased, to 2 per week. Plus provision of education and support sessions for families |  |

| Number | Activity | Elements | Status | Proposed outcomes | Achieved outcomes | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| 5. | Metabolic |  |  |  |  |  |
|  | Tayside |  |  |  |  |  |
|  |  | Consultant | Y September 09 – Locums are currently being used | Ensure the sustainability of the service | Sustained service provision | Locum support has sustained the provision of the service following retirement of academic involved it it’s provision |
|  |  | A&C Support | Y – January 09 |  |  |  |
|  |  | Dietician | Y – March 09 | To support the development of the national network and provide local support to children and young people | Some additional specialist clinics have been provide, asw ell as increased outreach support | The development of this post has been affected by the deal in the consultant taking up post |
|  |  | Specialist nurse | Y – April 09 | Increase in provision to the service and ability to develop nurse led clinics. Allow for training to other staff | Is providing local support to children and young people , and providing educational support to families | The development of this post has been affected by the deal in the consultant taking up post |
|  |  | Psychology | Y – July 09 | Will provided addition support to children living with chronic health conditions |  |  |

| Number | Activity | Elements | Status | Proposed outcomes | Achieved outcomes | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| 6. | Oncology |  |  |  |  |  |
|  | Grampian |  |  |  |  |  |
|  |  | Nurse Specialist – Outreach | Had to go to 2nd round of recruitment –Being covered by additional hours by nursing team | Increase in provision to the service and ability to develop nurse led clinics. Allow for training to other staff | Limited support has been provided for an out reach service | This post will not be fully developed until the post holder is appointed |
|  |  | Consultant Oncologist | N in development process –Full time locum is being recruited as interim | Ensure the sustainability of the service |  | Currently attempting to recruit a full –time locum as interim measure |
|  |  | Speech & Language Therapist | Y Sept 09 | Will provided addition support to children living with chronic health conditions | Is providing a number of out reach and home support to children and families |  |
|  |  | Health Psychologist | N in recruitment process – Additional hours being provided by service to cover | Will provided addition support to children living with chronic health conditions |  | Limited support is being provided by service until post is recruited to |
|  |  | Pharmacist | N in recruitment process - Additional hours being provided by service | Will provided addition support to children living with chronic health conditions |  | Limited support is being provided by service until post is recruited to |

| Number | Activity | Elements | Status | Proposed outcomes | Achieved outcomes | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| 6. | Oncology |  |  |  |  |  |
|  | Highland |  |  |  |  |  |
|  |  | Nurse Specialist | Y - April 09 | Increase in provision to the service and ability to develop nurse led clinics. Allow for training to other staff | Has established an out reach service to support children/young people and families |  |
|  |  | Staff Nurse | Y – April 09 | To sustain nursing support with ward | Additional investment has help sustain oncoclogy nursing support on ward |  |
|  |  | Admin | Y- April 09 |  |  |  |

| Number | Activity | Elements | Status | Proposed outcomes | Achieved outcomes | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| 6. | Oncology |  |  |  |  |  |
|  | Tayside |  |  |  |  |  |
|  |  | Consultant Oncologist | Y - December 09 | Ensure the sustainability of the service | Additional investment will sustain provision of service |  |
|  |  | Occupational Therapist | N in recruitment process | Will provided addition support to children living with chronic health conditions |  | This post will not be fully developed until the post holder is appointed |
|  |  | Speech & Language Therapist | N in recruitment process Cover by additional hours | Will provided addition support to children living with chronic health conditions |  | This post will not be fully developed until the post holder is appointed |
|  |  | Outreach Nursing | N in recruitment process – Cover by additional hours | Increase in provision to the service and ability to develop nurse led clinics. Allow for training to other staff |  | This post will not be fully developed until the post holder is appointed |
|  |  | Health Psychologist | N in recruitment process - – Cover by additional hours | Will provided addition support to children living with chronic health conditions |  | This post will not be fully developed until the post holder is appointed |
|  |  | Pharmacist | N in recruitment process– Cover by additional hours | Will provided addition support to children living with chronic health conditions |  |  |

| Number | Activity | Elements | Status | Proposed outcomes | Achieved outcomes | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| 7. | Rheumatology |  |  |  |  |  |
|  | Grampian |  |  |  |  |  |
|  |  | Nurse Specialist - Grampian | Y –June 09 | Increase in provision to the service and ability to develop nurse led clinics. Allow for training to other staff | Has increased support to out reach clinical service and has introduced 3 nurse led clinics |  |
|  |  | Physiotherapist – Grampian | No - In the recruitment process | Will provided addition support to children living with chronic health conditions |  | The service has been providing some additional support to nurse led clinics, but post and role have not been fully developed |
|  |  | Occupational Therapist - Grampian | No - In the recruitment process | Will provided addition support to children living with chronic health conditions |  | The service has been providing some additional support to nurse led clinics, but post and role have not been fully developed |
|  |  | A&C Support, Grampian | Y – February 09 |  |  |  |
|  | Highland |  |  |  |  |  |
|  |  | Physiotherapist - Highland | Y – March 09 | To support the regional network and provide care locally | Has been supporting the outreach clinics and providing local follow-up clinics |  |

| Number | Activity | Elements | Status | Proposed outcomes | Achieved outcomes | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| 7. | Rheumatology |  |  |  |  |  |
|  | Tayside |  |  |  |  |  |
|  |  | Nurse Specialist - Tayside | Y – May 09 |  |  |  |
|  |  | Physiotherapist - Tayside | Y – April 09 | To support the regional network and provide care locally | Has been supporting the outreach clinics and providing local follow-up clinics |  |
|  |  | Occupational Therapist , Tayside | Y – April 09 | To support the regional network and provide care locally | Has been supporting the outreach clinics and providing local follow-up clinics |  |
|  |  | Psychology – Tayside | No - In the recruitment process |  |  |  |
|  |  | A&C Support, Tayside | Y – January 09 | To support clinical service provision |  |  |
|  |  | Consultant Input - Tayside | Y – this is linked to purchase of outreach time | To allow development of tertiary pout reach service | Has led to establishment of a consultant led outreach service from Yorkhill |  |

| Number | Activity | Elements | Status | Proposed outcomes | Achieved outcomes | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| 8. | Respiratory |  |  |  |  |  |
|  | Grampian |  |  |  |  |  |
|  |  | Clinical Leader | Y January 09 | To support the development of regional network | Providing clinical leadership to network and supporting development of NDP proposals |  |
|  |  | Provision of outreach service to NHS Highland | Y – March 09 | To provide a tertiary outreach service allowing improved access | Two outreach clinics have been establish and ar support by local clinic team |  |
|  |  | Specialist Nursing | Y – Sept 09 | Increase in provision to the service and ability to develop nurse led clinics. Allow for training to other staff | Has increased support to out reach clinical service and has introduced weekly nurse led clinics |  |
|  |  | Physiotherapist | No - In the recruitment process – held up in vacancy control | Will provided addition support to children living with chronic health conditions |  | The service has been providing some additional support to nurse led clinics, |
|  |  | Dietician | Y - July 09 | To support the regional network and provide care locally | Has been supporting the outreach clinics and providing local follow-up clinics |  |

| Number | Activity | Elements | Status | Proposed outcomes | Achieved outcomes | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| 8. | Respiratory |  |  |  |  |  |
|  | Highland |  |  |  |  |  |
|  |  | Specialist nurse for NHS Highland | Y posted redesigned 50/50 split dietetic and nursing | To support the regional network, outreach service and provide care locally | Has been supporting the outreach clinics and providing local follow-up clinics | This funding was split into two 0.5 posts |
|  |  | A&C Support, NHS Highland | Y – January 09 | To support the regional network and provide care locally |  |  |
|  | Tayside |  |  |  |  |  |
|  |  | Consultant respiratory paediatrician | December 09 | To ensure the sustainability of the service | The service has been maintained and post holder is contributing to the development of eth regional network and outreach services |  |
|  |  | Dietician | March 09 | To support the regional network and provide care locally | Has been supporting the outreach clinics and providing local follow-up clinics |  |
|  |  | A&C Support | December 09 | To support clinical service provision |  |  |