National Delivery Plan Year 2 Financial Update: Quarter 4

West of Scotland

Summary:

Total allocated 2009/10 : £3,513,000 Predicted spend in Q4: £1,086,750 Actual spend in Q4: £ £1,021,250 Spend in Q4 against predicted spend (as +/- %): 94% Cumulative spend: £ 3,093,000 Money remaining: £420,000 Slippage forecast as at Q3: £420,000 Revised slippage forecast: £ 420,000 Number of vacant posts (including those being covered by locums, additional hours etc.):

| Regional | Allocated | Q1 Spent | Q2 Projected | Q2 Spent | Q3 Projected | Q3 Spent | Q4 Projected (as at Q3) | Q4 Spent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Infrastructure | 105,000 | 26.25 | 26.25 | 26.25 | 26.25 | 26.5 | 26.25 | 26.25 |
| Gastro intestinal | 594,000 | 48 | 124 | 113 | 175.5 | 130 | 211 | 181 |
| Child Protection | 298,000 | 54 | 57 | 53.5 | 53.5 | 53.5 | 53.5 | 53.5 |
| Orthopaedic Surgery | 326,000 | 86 | 88 | 80 | 88 | 88 | 88 | 88 |
| Neurology/epilepsy | 45,000 | 0 | 5 | 0 | 18.5 | 18.5 | 18.5 | 18.5 |
| General Surgery | 180,000 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |
| Pan-Scotland |  |  |  |  |  |  |  |  |
| Metabolic | 18,000 | 0 | 2 | 2 | 5 | 2 | 5 | 5 |
| Cancer | 652,000 | 190 | 199 | 230 | 230 | 180 | 230 | 230 |
| Rheumatology | 308,000 | 11 | 50 | 17 | 62 | 21.5 | 84 | 84 |
| Complex respiratory | 315,000 | 41 | 47 | 54 | 72 | 39 | 113.5 | 88 |
| Cystic Fibrosis | 349,000 | 9 | 56 | 57 | 81 | 75 | 107 | 107 |
| Forth Valley Cystic Fibrosis | 39,000 | 0 | 0 | 0 | 10 | 10 | 10 | 10 |
| Endocrine | 284,000 | 42 | 64 | 76 | 98 | 87 | 105 | 95 |
| TOTAL | 3,513,000 | 552.25 | 763 | 753.75 | 959.75 | 765.75 | 1086.75 | 1021.25 |

| Infrastructure £105,000 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Post | Appointed? Y/N Date of appointment | Q1 Spent | Q2 Projected | Q2 Spent | Q3 Projected | Q3 Spent | Q4 Projected | Q4 Spent |
| Full time planning manager | In Post | 26.25 | 26.25 | 26.25 | 26.25 | 26.5 | 26.25 | 26.25 |
| Clinical backfill |  |  |  |  |  |  |  |  |

| Gastro Intestinal £594,000 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Post | Appointed? Y/N Date of appointment | Q1 Spent | Q2 Projected | Q2 Spent | Q3 Projected | Q3 Spent | Q4 Projected | Q4 Spent |
| RHSC |  |  |  |  |  |  |  |  |
| 2 WTE pathology | April 2008 | 27 | 27 | 27 | 27 | 27 | 27 | 27 |
| 3 WTE nurse specialists | Sept 09/Jan 10 | 0 | 10 | 10 | 21 | 10 | 31 | 11 |
| 2 WTE dieticians | Sept 09/Jan 10 | 0 | 7 | 7 | 21 | 7 | 21 | 21 |
| 1 WTE PGHN consultant | October 2009 | 0 | 35 | 35 | 35 | 35 | 35 | 35 |
| DGH |  |  |  |  |  |  |  |  |
| 2 PAs for each DGH | June 2009 | 9 | 24 | 19 | 25 | 22 | 32 | 32 |
| 2.1 WTE dieticians | July 2009 | 0 | 12 | 6 | 19.5 | 15 | 23 | 23 |
| 2.1 WTE nurse specialists | July 2009/Jan 10 | 0 | 9 | 9 | 27 | 14 | 42 | 32 |
| Total spent/predicted |  | 48 | 124 | 113 | 175.5 | 130 | 211 | 181 |

| Child Protection £298,000 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Post | Appointed? Y/N Date of appointment | Q1 Spent | Q2 Projected | Q2 Spent | Q3 Projected | Q3 Spent | Q4 Projected | Q4 Spent |
| 2.6 WTE consultant paediatricians | April – Sept 2009 | 54 | 57 | 53.5 | 53.5 | 53.5 | 53.5 | 53.5 |
| Total spent/predicted |  | 54 | 57 | 53.5 | 53.5 | 53.5 | 53.5 | 53.5 |

| Orthopaedic Surgery £326,000 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Post | Appointed? Y/N Date of appointment | Q1 Spent | Q2 Projected | Q2 Spent | Q3 Projected | Q3 Spent | Q4 Projected | Q4 Spent |
| Consultant RHSC | Substantive appointee in post | 40 | 34 | 34 | 34 | 34 | 34 | 34 |
| Clinical nurse specialist | April 2008 | 21 | 21 | 21 | 21 | 21 | 21 | 21 |
| Theatre time – RHSC consultant post | April 2009 | 25 | 25 | 25 | 25 | 25 | 25 | 25 |
| DGH outreach sessions to NHS A&A | Sept 2009 | 0 | 8 | 0 | 8 | 8 | 8 | 8 |
| Total spent/predicted |  | 86 | 88 | 80 | 88 | 88 | 88 | 88 |

| Neurology/Epilepsy £45,000 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Post | Appointed? Y/N Date of appointment | Q1 Spent | Q2 Projected | Q2 Spent | Q3 Projected | Q3 Spent | Q4 Projected | Q4 Spent |
| 1.0 WTE paediatric nurse | July 2009 | 0 | 4 | 0 | 16.5 | 16.5 | 16.5 | 16.5 |
| 0.2 WTE admin and clerical | Nov 2009 | 0 | 1 | 0 | 2 | 2 | 2 | 2 |
| Total spent/predicted |  | 0 | 5 | 0 | 18.5 | 18.5 | 18.5 | 18.5 |

| General Surgery £180,000 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Post | Appointed? Y/N Date of appointment | Q1 Spent | Q2 Projected | Q2 Spent | Q3 Projected | Q3 Spent | Q4 Projected | Q4 Spent |
| 2.6 WTE consultant paediatricians | Outreach going on from 2008 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |
| Total spent/predicted |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 |

| Metabolic £18,000 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Post | Appointed? Y/N Date of appointment | Q1 Spent | Q2 Projected | Q2 Spent | Q3 Projected | Q3 Spent | Q4 Projected | Q4 Spent |
| Dietetic support | Nov 2009 | 0 | 2 | 2 | 5 | 2 | 5 | 5 |
| Total spent/predicted |  | 0 | 2 | 2 | 5 | 2 | 5 | 5 |

| Cancer £652,000 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Post | Appointed? Y/N Date of appointment | Q1 Spent | Q2 Projected | Q2 Spent | Q3 Projected | Q3 Spent | Q4 Projected | Q4 Spent |
| Medical | 2008/2009 | 41 | 35 | 35 | 35 | 35 | 35 | 35 |
| Specialist Nursing | April 2009/Sept 2009/Jan 10 | 21 | 28 | 31 | 41 | 31 | 41 | 41 |
| Ward nursing | April 2009 | 94 | 94 | 120 | 120 | 90 | 120 | 120 |
| Outreach nurses | May 2009 | 17 | 25 | 17 | 17 | 17 | 17 | 17 |
| Data management | April 2009 | 17 | 17 | 17 | 17 | 17 | 17 | 17 |
| Total spent/predicted |  | 190 | 199 | 230 | 230 | 190 | 230 | 230 |

| Rheumatology £308,000 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Post | Appointed? Y/N Date of appointment | Q1 Spent | Q2 Projected | Q2 Spent | Q3 Projected | Q3 Spent | Q4 Projected | Q4 Spent |
| 1 WTE nurse consultant | Jan 2010 | 0 | 4 | 0 | 0 | 0 | 14 | 14 |
| 2.75 WTE clinical nurse specialists | June 2009 onwards | 9 | 21 | 12.5 | 41 | 12.5 | 41 | 41 |
| 1 WTE adolescent/transition nurse | Jan 2010 | 0 | 4 | 0 | 10 | 0 | 14 | 14 |
| 1.8 AHP | June 2009 onwards | 2 | 21 | 4. 5 | 11 | 9 | 15 | 15 |
| Total spent/predicted |  | 11 | 50 | 17 | 62 | 21.5 | 84 | 84 |

| Complex Respiratory £315,000 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Post | Appointed? Y/N Date of appointment | Q1 Spent | Q2 Projected | Q2 Spent | Q3 Projected | Q3 Spent | Q4 Projected | Q4 Spent |
| Network | April 2009 | 20 | 20 | 20 | 20 | 20 | 20 | 20 |
| Nurse specialists | Jan 2010 | 0 | 6 | 2 | 12 | 0 | 38 | 18 |
| Physiotherapy | Oct 2009 onwards | 0 | 0 | 11 | 16 | 10 | 28.5 | 23 |
| Physiology | April 2009 onwards | 21 | 21 | 21 | 24 | 9 | 27 | 27 |
| Total spent/predicted |  | 41 | 47 | 54 | 72 | 39 | 113.5 | 88 |

| Cystic Fibrosis £349,000 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Post | Appointed? Y/N Date of appointment | Q1 Spent | Q2 Projected | Q2 Spent | Q3 Projected | Q3 Spent | Q4 Projected | Q4 Spent |
| Medical | Sept 2009 | 0 | 15 | 15 | 15 | 14 | 15 | 15 |
| Specialist nursing | July 2009 | 0 | 18 | 2 | 11 | 21 | 11 | 11 |
| Dietician | June 2009 | 9 | 9 | 21 | 21 | 21 | 21 | 21 |
| Physiotherapist | July 2009 onwards | 0 | 10 | 19 | 19 | 16 | 26 | 26 |
| Other AHP | Jan 2010 | 0 | 1 | 0 | 6 | 0 | 13 | 13 |
| Data management | July 2009 | 0 | 0 | 0 | 7 | 4 | 7 | 7 |
| Diagnostics | July 2009 | 0 | 3 | 0 | 9 | 9 | 14 | 14 |
| Total spent/predicted |  | 9 | 56 | 57 | 88 | 75 | 107 | 107 |

| Forth Valley Cystic Fibrosis £39,000 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Post | Appointed? Y/N Date of appointment | Q1 Spent | Q2 Projected | Q2 Spent | Q3 Projected | Q3 Spent | Q4 Projected | Q4 Spent |
| (Please insert details) | October 2009 | 0 | 0 | 10 | 10 | 10 | 10 | 10 |
| Total spent/predicted |  | 0 | 0 | 10 | 10 | 10 | 10 | 10 |

| Endocrine £284,000 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Post | Appointed? Y/N Date of appointment | Q1 Spent | Q2 Projected | Q2 Spent | Q3 Projected | Q3 Spent | Q4 Projected | Q4 Spent |
| Consultant sessions | June 2009 onwards | 0 | 6 | 20 | 21 | 21 | 21 | 21 |
| Nurse specialist to RHSC | April/Sept 2009 | 10 | 14 | 14 | 25 | 15 | 25 | 15 |
| Nurse specialists spread across DGH’s | June 2009 onwards | 4 | 9 | 7 | 13 | 11 | 18 | 18 |
| AHP development for OT to RHSC | April 2009 | 6 | 6 | 6 | 6 | 6 | 6 | 6 |
| AHP development for dietetics to RHSC | Sept 2009 | 0 | 4 | 3 | 7 | 7 | 7 | 7 |
| AHP development for OT support across DGHs | June 2009 onwards | 2 | 3 | 3 | 3 | 4 | 4 | 4 |
| AHP development for dietetic support across DGHs | June 2009 onwards | 0 | 2 | 3 | 3 | 3 | 4 | 4 |
| Densitometrist for regional DXA service at RHSC | April 2009 | 20 | 20 | 20 | 20 | 20 | 20 | 20 |
| Total spent/predicted |  | 42 | 64 | 76 | 98 | 87 | 105 | 95 |
| TOTAL ALL SERVICES SPENT/ PREDICTED |  | 552025 | 763 | 753.75 | 976.75 | 781 | 1086.75 | 1021.25 |

Commentary (please provide explanation of spending to date) Expenditure on CF for Forth Valley has been excluded form calculations as this is funded via SEAT and not WoS allocation.

Key Achievements this quarter? - Consolidation of outreach General Paediatric Surgical clinics and operating lists in Stirling and Wishaw - Appointment of cancer posts at RHSC including Consultant with interest in teenagers and young adults and nurse specialists - Additional 6 cancer beds staffed in RHSC Glasgow - 3rd Tertiary Child Protection Consultant appointed in GGC - Commissioning of West of Scotland Regional MCN’s for Gastroenterology and Respiratory Medicine including appointment of Clinical Leads and Network managers - Community Nursing post created in Dumfries covering Gastroenterology, Rheumatology and Endocrinology - Increased access to local Physiotherapy provision in Stirling for children with Rheumatological or Respiratory problems - The appointment of an Epilepsy Nurse Specialist enabling Ayrshire & Arran to comply with SIGN Guidelines