National Delivery Plan for Specialist Children’s Services

Implementation Group Meeting

29 October 2010

ACTION POINTS

| AGENDA ITEM | NUMBER | ACTION | RESPONSIBLE | DEADLINE (if not specified, a date has been suggested) | STATUS | COMMENTS |
| --- | --- | --- | --- | --- | --- | --- |
| 2 | 1 | Liaise with Catriona Johnson and SG colleagues regarding integrating MCNs + regional planning | Lucy Colquhoun | January 2011 | Outstanding | To be included in transition event (see below) |
| 2 | 2 | Progress planning for 1 day transition event | Deirdre Evans with SG | 12 November 2010 | Outstanding | Catriona Johnson to give update on progress at 13 Jan mtg |
| 3 | 1 | To contact Fiona Dagge-Bell regarding QIS’ role in performance indicators | Deirdre Evans | 12 December 2010 | Complete | Fiona Dagg-Bell confirmed no QIS involvement |
| 3 | 2 | Produce a progress report from MCNs based on 5 core indicators | Deirdre Evans with ISD | January 2011 | Agenda item for 13 Jan |  |
| 4 | 1 | Set up meeting for January to discuss how to fill vacant posts and write strategy (regions, clinical leads and others) | Lucy Colquhoun | 12 November 2010 | Complete: meeting arranged for 24 Jan |  |
| 4 | 2 | Submit NES proposal for 2011/12 funding of non-recurrent projects requiring additional support | Mary Boyle | December 2010 | Complete: agenda item for 13 Jan |  |
| 7 | 1 | Meet to discuss final draft of DGH competencies paper before submitting to NDPIG (to include paediatric general surgery provision) | Jim Beattie and John Froggatt | End of November 2010 | Complete: meeting arranged for 7 Jan |  |
| 8 | 1 | Provide 6 monthly updates on patient safety programme to NDPIG | Julie Adams |  | Ongoing |  |
| 9 | 1 | Link to guidance for funding major adaptations for children and young people to be added to the minutes for circulation | Stewart Squire | 12 November 2010 | Complete |  |
| 10 | 1 | Include article on Remote and Rural progress in next NDP Newsletter | Lucy Colquhoun | February 2011 | In progress | Ken Mitchell to provide text |
| 11 | 1 | Forward Consultation for Specialty Training intake numbers and send further information on funding arrangements to specialty trainees on to Eddie Doyle | Kerry Chalmers | 5 November 2010 | Complete |  |
| 11 | 2 | Issues around decoupling of training to be raised with RCPCH | Jim Beattie |  | Ongoing |  |