## Sheet1
National Delivery Plan Year 2 financial update
National Services Division (including cancer services)
Summary:
| Total allocated 2009/10 : £790,250 | Currently vacant posts are as follows:
Predicted Spend in Q4: £265.572
| Total spent in Q4: £237,225 | The 2.5w.t.e. band5 Network Analysts
| Slippage in Q4 against predicted spend (as %): 10.7% | The Admin support for the Tayside CF Network
Cumulative spend to date: £605,868
Money remaining: £184,382
N.B. £15k of this is identified underspend (not slippage). It was agreed that this would fund a 0.5wte Band5 Analyst for the Children's Cancer Service Network in Tayside.
Children with Complex Needs MCN £126,000
| Item (e.g. data collection, training needs analysis, etc) | Appointed? | Q1 Spent | Q2 Spent | Q3 Spent | Q4 Projected | Forecast for 2009/10
Y/N
Date of Appointment
| Lead Clinician - 2PAs | 2009-04-01 | 4000 | 4273 | 4250 | 3998 | 16521
| Network Manager 0.5w.t.e. | 2009-04-01 | 4000 | 7441 | 7500 | 4886 | 23827 | 3k less than forecast, as bottom of scale
| Nurse Specialist |  | 0 | 0 | 0 | 0 | 0
| Administrator - 1.0w.t.e. | 2009-11-02 | 0 | 0 | 4707 | 3483 | 8190 | savings from use of shared admin resource
| Travel & Meeting Costs |  | 0 | 0 | 316 | 3188 | 3504
| Printing & Stationery |  | 500 | 300 | 300 | 188 | 1288
| Overheads |  | 0 | 260 | 420 | 420 | 1100
| Training |  | 0 | 0 | 250 | 1418 | 1668
| Telephones & Postage |  | 100 | 250 | 550 | 140 | 1040
| Education Module |  |  |  | 4000 | 5600 | 9600
| Set up Costs (I.T. & Furniture) |  | 2500 | 1000 | 0 | 1392 | 4892
| Total spent/predicted |  | 11100 | 13524 | 22293 | 24713 | 71630
Cystic Fibrosis MCN £85,500
| Item | Appointed? | Q1 Spent | Q2 Spent | Q3 Spent | Q4 Projected | Forecast for 2009/10
Y/N
Date of Appointment
| Lead Clinician - 2PAs | 2009-06-01 | 0 | 1000 | 3000 | 1000 | 5000
| Network Manager 0.5w.t.e. | 2009-12-01 | 0 | 0 | 899 | 4745 | 5644
| Administrator - 1.0w.t.e. | Recruitment in progress | 0 | 0 | 0 | 2023 | 2023
| Travel & Meeting Costs |  | 0 | 500 | 250 | 278 | 1028
| Printing & Stationery |  | 0 | 250 | 750 | 1250 | 2250
| Overheads |  | 750 | 750 | 750 | 750 | 3000
| Training |  | 0 | 0 | 350 | 7 | 357
| Telephones & Postage |  | 0 | 150 | 0 | 0 | 150
| Set up Costs (I.T. & Furniture) |  | 1250 | 1250 | 750 | 0 | 3250
| Total spent/predicted |  | 2000 | 3900 | 6749 | 10053 | 22702
Paediatric Rheumatology £85,000
| Item | Appointed? | Q1 Spent | Q2 Spent | Q3 Spent | Q4 Projected | Forecast for 2009/10
Y/N
Date of Appointment
| Lead Clinician - 2PAs | 2009-04-01 | 5000 | 5000 | 5000 | 5000 | 20000
| Network Manager 0.5w.t.e. | 2009-04-01 | 6000 | 5500 | 5500 | 5500 | 22500
| Administrator - 1.0w.t.e. | 2009-04-01 | 7250 | 7250 | 7250 | 7250 | 29000
| Travel & Meeting Costs |  | 1750 | 1500 | 1400 | 1250 | 5900
| Printing & Stationery |  | 750 | 1000 | 750 | 750 | 3250
| Overheads |  | 750 | 750 | 750 | 750 | 3000
| Training |  | 400 | 0 | 400 | 400 | 1200
| Telephones & Postage |  | 350 | 400 | 300 | 300 | 1350
| Set up Costs (I.T. & Furniture) |  | 2500 | 0 | 0 | 0 | 2500
| Total spent/predicted |  | 24750 | 21400 | 21350 | 21200 | 88700
Paediatric Endocrinology £85,000
| Item | Appointed? | Q1 Spent | Q2 Spent | Q3 Spent | Q4 Projected | Forecast for 2009/10
Y/N
Date of Appointment
| Lead Clinician - 2PAs | 2009-04-01 | 5000 | 5000 | 6000 | 6000 | 22000
| Network Manager 0.5w.t.e. | 2009-04-01 | 5900 | 5900 | 5900 | 5900 | 23600
| Administrator - 1.0w.t.e. | 2009-04-01 | 6800 | 6800 | 6800 | 6800 | 27200
| Travel & Meeting Costs |  | 1400 | 1600 | 1250 | 1250 | 5500
| Printing & Stationery |  | 1250 | 1500 | 750 | 750 | 4250
| Overheads |  | 750 | 750 | 750 | 750 | 3000
| Training |  | 400 | 200 | 350 | 350 | 1300
| Telephones & Postage |  | 550 | 500 | 450 | 450 | 1950
| Set up Costs (I.T. & Furniture) |  | 2500 | 0 |  |  | 2500
| Total spent/predicted |  | 24550 | 22250 | 22250 | 22250 | 91300
Outcomes – ISD £80,500
| Item | Appointed? | Q1 Spent | Q2 Spent | Q3 Spent | Q4 Projected | Forecast for 2009/10
Y/N
Date of Appointment
| 2 w.t.e. Data Analysts | In post since last financial year | 18759 | 18759 | 18759 | 18759 | 75036
| Total spent/predicted |  | 18759 | 18759 | 18759 | 18759 | 75036
Database for MCNs £240,000
| Item | Appointed? | Q1 Spent | Q2 Spent | Q3 Spent | Q4 Projected | Forecast for 2009/10
Y/N
Date of Appointment
| Project Manager | In post since last financial year | 11250 | 11250 | 11250 | 11250 | 45000
| I.T. Consultancy & Procurement Expertise (NISG) |  | 12500 | 36000 | 36000 |  | 84500
| System Revenue Costs (Maint & Cap Chgs etc.) |  | 0 |  |  | 125000 | 125000
| Total spent/predicted |  | 23750 | 47250 | 47250 | 136250 | 254500
*** | Network Data Analysts
84000
| Item | Appointed? | Q1 Spent | Q2 Spent | Q3 Spent | Q4 Projected | Forecast for 2009/10
Y/N
Date of Appointment
| 1.0 w.t.e. Band 5 Analyst (GG+C) | Recruitment process underway | 0 | 0 | 0 | 800 | 800 | Vacant
| 1.0 w.t.e. Band 5 Analyst (Tayside) | Job Description still with evaluation team |  | 0 | 0 |  | 0
| 0.5 w.t.e. Band 5 Analyst (Lothian) | Recruitment process underway |  | 0 | 0 | 1200 | 1200
| Total spent/predicted |  | 0 | 0 | 0 | 2000 | 2000
Cancer Summary:
| Total allocated 2009/10 : £337,100 | There are no vacant posts
Predicted spend in Q4: £88,525
Total spent in Q4: £85,225
Slippage in Q4 against predicted spend (as %): nil
Cumulative spend to date: £270,100
Money remaining: £67,000
| Cancer services | Total awarded £337,100
| MSN Childrens Cancer | 147000
| Post | Appointed? Y/N | Q1 Spent | Q2 Spent | Q3 Spent | Q4 Projected | Forecast for 2009/10
Date of appointment
| MDT co-ordinator and support £79,000 | 2009-09-28 | 0 | 3000 | 18000 | 20000 | 41000
| Late effects project £28,550 | 2009-12-01 | 0 | 2000 | 6750 | 7250 | 16000
| Palliative care £28,000 | 2009-11-02 | 500 | 1750 | 7000 | 7000 | 16250
| Admin support £11,450 | 2009-10-01 | 0 |  |  | 3000 | 3000
| Network Analyst (0.5 Band5) - funded from £84k |  |  |  |  | 3750 | 3750
| Total spent/predicted |  | 500 | 6750 | 31750 | 41000 | 80000 | Transferred to Tayside in March 2010
Financial reports on actual spend
to come from NoSPG
| Bone Marrow Development | 190100
| Post | Appointed? Y/N | Q1 Spent | Q2 Spent | Q3 Spent | Q4 Projected | Forecast for 2009/10
Date of appointment
| Data Manager – A4C Band 6 |  | 8525 | 8525 | 8525 | 8525 | 34100
| Nurse Specialist – A4C Band 7 |  | 10200 | 10200 | 10200 | 10200 | 40800
| Costs attributable to the BMT services |  | 28800 | 28800 | 28800 | 28800 | 115200
| Total spent/predicted |  | 47525 | 47525 | 47525 | 47525 | 190100 | Transferred to GG+C in March
| Cancer total spent/predicted |  | 48025 | 54275 | 79275 | 88525 | 270100
| TOTAL ALL SERVICES SPENT/PREDICTED |  | 152934 | 181358 | 217926 | 323750 | 875968
[6 empty] | Full Year Forecast | 875968
[6 empty] | Full Year Funding | 1127350
[6 empty] | Slippage | 251382
| Commentary (please provide explanation of spending to date) |  |  |  |  | Returned to SGHD | 200000
Initially the £84k allocation for 'Network Data Analysts' was to fund 2.5wte Band 7 posts.
These posts were advertised at Band 5, and it was agreed that the underspend would fund a further 0.5wte Band 5 post in Tayside, to compliment the Childrens' Cancer MSN.
NSD are now expecting the year end position to show an underspend of £243k. This should not change significantly, as most year end adjustsments have now been made.
This underspend is larger than forecast at Q3, because of further slippage with the Network Analyst posts. This further slippage was always likely, and was mentioned in the Q3 report.
The underspend is, in the main, due to four contributing factors:
The delay in recruiting the 2.5w.t.e. band5 Network Analysts, which are still not in post - 82k underspent
The MSN in Tayside only incurred set up costs in the 1st half of the year, before getting off the ground in October - 67k underspent
There was also delay in getting the CF (Tayside) network established - 63k
The nurse specialist originally attached to the Lothian network was not recruited (as this was deemed surplus to requirements) - 41k
The net effect of these four factors is reduced from 253k to around 243k, by the slight overspends elsewhere.
These are, in the main, due to Network set up costs and the extra activity that Networks incur in the first year. These overspends are unlikely to recur.