National Delivery Plan Year 2 Financial Update: Quarter 4

South East and Tayside Regional Planning Group

Summary:

Total allocated 2009/10 : £1,608,000 Predicted spend Q4: £380,305 Actual spend Q4: £404,216 Spend in Q4 against predicted spend (as +/- %): +6% Cumulative spend to date: £1,408,000 Slippage forecast as at Q3: £223,911 Revised slippage forecast: £200,000 Number of vacant posts (including those being covered by locums, additional hours etc.): 5.5

|  | Regional | Allocated | Q1 Spent | Q2 Projected | Q2 Spent | Q3 Projected | Q3 Spent | Q4 Projected | Q4 Spent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Gastroenterology | 204,000 | 0 | 19400 | 13500 | 25600 | 15,200 | 25600 | 25600 |
| 2 | General Surgery | 203,000 | 34961 | 48886 | 48886 | 50138 | 50138 | 50138 | 50138 |
| 3 | MCN for Child Sexual Abuse | 44,000 | 3000 | 8383 | 3427 | 10290 | 7148 | 12590 | 10952 |
| 4 | Rheumatology | 162,000 | 40500 | 40500 | 40500 | 40500 | 40500 | 40500 | 40500 |
| 5 | Cystic Fibrosis | 302,000 | 0 | 58413 | 22314 | 76059 | 54298 | 80817 | 77417 |
| 6 | Cancer | 309,000 | 50395 | 78213 | 77645 | 83055 | 81050 | 87860 | 87860 |
| 7 | Non Specialist Centres | 312,000 | 5752 | 32386 | 23886 | 68700 | 58500 | 61900 | 58500 |
| 8 | Psychology | 152,000 | 0 | 19200 | 12400 | 20900 | 17500 | 20900 | 17500 |
|  | Restriction to ‘fair share’ | -80,000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
|  | Non-recurring (posts / training/ equipment) |  | 129785 | 121132 | 172500 | 85594 | 0 | 0 | 35749 |
|  | Total | 1,608,000 | 264393 | 426513 | 415057 | 460836 | 324334 | 380305 | 404216 |

| Gastroenterology £204,000 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Post | Appointed? Y/N Date of appointment | Q1 Spent | Q2 Projected | Q2 Spent | Q3 Projected | Q3 Spent | Q4 Projected | Q4 Spent |
| NHS Lothian |  |  |  |  |  |  |  |  |
| Consultant Gastroenterologist | Y May 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Dietician | Y July 09 | 0 | 7000 | 10500 | 10500 | 10500 | 10500 | 10500 |
| Nurse | Y Feb 10 | 0 | 7000 | 0 | 7000 | 0 | 7000 | 7000 |
| Pharmacist | Y July 09 | 0 | 2000 | 3000 | 3000 | 3000 | 3000 | 3000 |
| NHS Fife |  |  |  |  |  |  |  |  |
| Dietician | Y Dec 09 | 0 | 3400 | 0 | 5100 | 1700 | 5100 | 5100 |
| Total spent/predicted |  | 0 | 19400 | 13500 | 25600 | 15200 | 25600 | 25600 |

| General Surgery £203,000 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Post | Appointed? Y/N Date of appointment | Q1 Spent | Q2 Projected | Q2 Spent | Q3 Projected | Q3 Spent | Q4 Projected | Quarter 4 Spent |
| NHS Lothian |  |  |  |  |  |  |  |  |
| Paediatric Surgeon | Y Sept 08 | 28750 | 28750 | 28750 | 28750 | 28750 | 28750 | 28750 |
| Travel |  | 500 | 500 | 500 | 500 | 500 | 500 | 500 |
| NHS Fife |  |  |  |  |  |  |  |  |
| Nurse |  | 461 | 1383 | 1383 | 1383 | 1383 | 1383 | 1383 |
| Theatre Session x1 PW |  | 5250 | 15750 | 15750 | 15750 | 15750 | 15750 | 15750 |
| NHS Borders |  |  |  |  |  |  |  |  |
| Nursing |  |  | 2503 | 2503 | 3755 | 3755 | 3755 | 3755 |
| Total spent/predicted |  | 34961 | 48886 | 48886 | 50138 | 50138 | 50138 | 50138 |

| MCN Child Sexual Abuse £44,000 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Post | Appointed? Y/N Date of appointment | Q1 Spent | Q2 Projected | Q2 Spent | Q3 Projected | Q3 Spent | Q4 Projected | Q4 Spent |
| Network development manager | Y Nov 09 | 0 | 3412 | 0 | 3833 | 3968 | 5952 | 5952 |
| Lead clinician | Y April 09 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 |
| Admin support | Y May 10 | 0 | 1637 | 427 | 2457 | 180 | 1638 | 0 |
| Travel and subsistence |  | 0 | 167 | 0 | 500 | 0 | 1000 | 1000 |
| Office costs |  | 0 | 167 | 0 | 500 | 0 | 1000 | 1000 |
| Total spent/predicted |  | 3000 | 8383 | 3427 | 10290 | 7148 | 12590 | 10952 |

| Rheumatology £162,000 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Post | Appointed? Y/N Date of appointment | Q1 Spent | Q2 Projected | Q2 Spent | Q3 Projected | Q3 Spent | Q4 Projected | Q4 Spent |
| NHS Lothian |  |  |  |  |  |  |  |  |
| Consultant (shared post with WoS) | Y Feb 09 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 |
| Nurse | Y Oct 08 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 |
| Physiotherapist | Y Oct 08 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 |
| Travel |  | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 |
| Total spent/predicted |  | 40500 | 40500 | 40500 | 40500 | 40500 | 40500 | 40500 |

| Cystic Fibrosis £302,000 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Post | Appointed? Y/N Date of appointment | Q1 Spent | Q2 Projected | Q2 Spent | Q3 Projected | Q3 Spent | Q4 Projected | Q4 Spent |
| NHS Lothian |  |  |  |  |  |  |  |  |
| Specialty Doctor | Y Sept 09 | 0 | 10500 | 2625 | 15750 | 15750 | 15750 | 15750 |
| Pharmacist | Y July 09 | 0 | 4875 | 7313 | 7313 | 7313 | 7312 | 7312 |
| Dietician | Y July 09 | 0 | 2567 | 3850 | 3850 | 3850 | 3850 | 3850 |
| Physiotherapist b8a | Y Oct 09 | 0 | 8267 | 0 | 12400 | 12400 | 12400 | 12400 |
| Physiotherapist b6 | Y July 09 | 0 | 5684 | 8525 | 8525 | 8525 | 8525 | 8525 |
| Nurses | Asthma Specialist 1.0 wte start date - Feb 10 LTV Specialist 1.0 –recruitment ongoing (April 10) | 0 | 13600 | 0 | 13600 | 0 | 13600 | 10200 |
| Dietician | Y Dec 09 | 0 | 2720 | 0 | 2720 | 1360 | 4080 | 4080 |
| NHS Fife |  |  |  |  |  |  |  |  |
| Physiotherapist | Backfilled from Dec 09 – start date Jan 10 | 0 | 3400 | 0 | 3400 | 1700 | 5100 | 5100 |
| Dietician | Y Dec 09 | 0 | 3400 | 0 | 5100 | 1700 | 5100 | 5100 |
| Nurse | Y Dec 09 | 0 | 3400 | 0 | 3400 | 1700 | 5100 | 5100 |
| Total spent/predicted |  | 0 | 58413 | 22314 | 76058 | 54298 | 80817 | 77417 |

| Cancer £309,000 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Post | Appointed? Y/N Date of appointment | Q1 Spent | Q2 Projected | Q2 Spent | Q3 Projected | Q3 Spent | Q4 Projected | Q4 Spent |
| NHS Lothian |  |  |  |  |  |  |  |  |
| Consultant | Y March 09 | 28750 | 28750 | 28750 | 28750 | 28750 | 28750 | 28750 |
| Ward nurses | Y April 09 | 21645 | 21645 | 21645 | 21645 | 21645 | 21645 | 21645 |
| Outreach nurse | Y July 09 | 0 | 8525 | 8525 | 8525 | 8525 | 8525 | 8525 |
| Occupational therapist | Y July 09 | 0 | 5683 | 8525 | 8525 | 8525 | 8525 | 8525 |
| Specialist physiotherapist (b7) | Y July 09 | 0 | 6800 | 10200 | 10500 | 10200 | 10200 | 10200 |
| Dietician | Y Dec 09 | 0 | 3410 | 0 | 3410 | 1705 | 5115 | 5115 |
| Pharmacist | Y Dec 09 – Locum appointed | 0 | 3400 | 0 | 1700 | 1700 | 5100 | 5100 |
| Total spent/predicted |  | 50395 | 78213 | 77645 | 83055 | 81050 | 87860 | 87860 |

| Non Specialist Centres £312,000 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Post | Appointed? Y/N Date of appointment | Q1 Spent | Q2 Projected | Q2 Spent | Q3 Projected | Q3 Spent | Q4 Projected | Q4 Spent |
| NHS Fife |  |  |  |  |  |  |  |  |
| Consultant Paediatrician with specialist interest | Projected Sept 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| NHS Borders |  |  |  |  |  |  |  |  |
| Paediatric nurse practitioners | Y June 09 | 5752 | 22186 | 22186 | 24650 | 24650 | 24650 | 24650 |
| Consultant paediatrician with specialist interest | Y Oct 09 | 0 | 0 | 0 | 28750 | 28750 | 28750 | 28750 |
| Physiotherapist | Physio and SN Posts combined into a respiratory specialist post. Projected July 10 | 0 | 3400 | 0 | 5100 | 0 | 1700 | 0 |
| Dietician | Y Sept 09 | 0 | 3400 | 1700 | 5100 | 5100 | 5100 | 5100 |
| Specialist nurse | Physio and SN Posts combined into a respiratory specialist post. Projected July 10 | 0 | 3400 | 0 | 5100 | 0 | 1700 | 0 |
| Total spent/predicted |  | 5752 | 32,386 | 23886 | 68700 | 58500 | 61900 | 58500 |

| Psychology £152,000 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Post | Appointed? Y/N Date of appointment | Q1 Spent | Q2 Projected | Q2 Spent | Q3 Projected | Q3 Spent | Q4 Projected | Q4 Spent |
| NHS Lothian |  |  |  |  |  |  |  |  |
| Play therapist | 0.5wte appointed Oct 09 0.5wte being re-advertisied |  | 6800 | 0 | 8500 | 5100 | 8500 | 5100 |
| NHS Borders |  |  |  |  |  |  |  |  |
| Psychologist | Y July 09 |  | 12400 | 12400 | 12400 | 124000 | 12400 | 12400 |
| Total spent/predicted |  |  | 19200 | 12400 | 20900 | 17500 | 20900 | 17500 |

| Total overall spent/predicted |  | 264393 | 426513 | 415057 | 460836 | 324334 | 380305 | 404216 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

Commentary: Gastroenterology The Consultant Gastroenterologist post holder is due to start in May. General Surgery Repatriation of surgery to Fife started in June and to Borders in Aug. As highlighted in the Q1 report, the nursing support in Fife and Borders to support repatriation of general surgery represents an increase in working hours available to support theatre sessions rather than specific appointments. MCN for Child Sexual Abuse Interviews for the 0.5wte admin post were held in March with the successful candidate due to start in May. Cystic Fibrosis, Complex Respiratory & Long Term Ventilation Interviews for the LTV Nurse post are being held in April. The 0.5wte physiotherapist post in Fife was backfilled in December with the substantive post holder in place from January. Cancer The 0.5wte Pharmacist post is currently filled by a locum appointment. Non-specialist Centres Interviews were held in February and the successful candidate accepted and then declined the offer. The post is to be re-advertised with recruitment projected for September. Borders has combined the 0.5wte Physiotherapist and 0.5wte Specialist Nurse posts into a 1.0wte Respiratory Specialist post which has competencies that are suitable for candidates from either profession. The advertising closing date of this post was 7th April, with a projected start date of July. Psychology SEAT received funding for 1.0wte play therapist post. A 0.5wte post was recruited to in October and a 0.5wte post is in the recruitment process. Non-recurring Spend As confirmed at the NDP Implementation Group meeting on 10 March, SEAT have in Quarter 3 utilised Year 2 slippage to fund some of the non-recurring equipment requirements identified as part of the NDP Year 3 Critical Care proposal.

Key Achievements this quarter: Recruitment to a number of specialist nursing and AHP posts. The provision of a number of new outreach clinics, in particular for Cystic Fibrosis patients. Improved working between clinicians across the region and access to specialist knowledge with education and training being delivered and new protocols and pathways being developed and shared.